## Buisness Projection
BUSINESS PLAN AS AT 21/02/2014
| OVERHEAD | [6 empty] | LABOUR | [9 empty] | Weekly Labour Expenditure
| RENT: £/wk(so) | 632.7 | IT & UTILITIES: £/wk(s) | 150 |  |  |  | Ankita | Max | James | John | Sam | Paul | Prakurti | Zayyad | Steve | Roger | Projected Total | Actual total
Spring term weeks | RENT DUE |  | PAYMENT DUE |  |  | Spring term | Week
1 | - |  | - |  |  | 2014-01-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | - |  | - |  |  | 2014-01-13 | 2 | 100 | 75 | 75 | 75 | 37.5 | 50 | 87.5 | 62.5 | 100 | 37.5 | 700 | 700
3 | - |  | - |  |  | 2014-01-20 | 3 | 100 | 100 | 125 | 125 | 62.5 | 100 | 100 | 100 | 112.5 | 62.5 | 987.5 | 987.5 | Functional Spec due
4 | 2530.8 |  | - |  | RENT | 2014-01-27 | 4 | 187.5 | 187.5 | 187.5 | 50 | 87.5 | 100 | 137.5 | 125 | 50 | 131.25 | 1243.75 | 1243.75 | QA manual due; Business Plan
5 | - |  | - |  |  | 2014-02-03 | 5 | 187.5 | 187.5 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 1324.5 | 1300 | PWS
6 | - |  | 900 |  | UTILITY | 2014-02-10 | 6 | 187.5 | 187.5 | 187.5 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 1416.25 | 1612.5 | Tender presentation; Financial Report 1
7 | 1898.1 |  | - |  | RENT | 2014-02-17 | 7 | 95.75 | 95.75 | 95.75 | 187.5 | 187.5 | 95.75 | 187.5 | 187.5 | 187.5 | 187.5 | 1508 | 1890.25 | Contracts | Integration for first JIRA sprint
8 | - |  | - |  |  | 2014-02-24 | 8 | 187.5 | 187.5 | 187.5 | 95.75 | 187.5 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 1416.25 | 1525 | Financial report 2
9 | - |  | - |  |  | 2014-03-03 | 9 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 1141 | 1637.5 | First Iteration complete; documents sent to supervisor; Integration and testing
10 | 1898.1 |  | 450 |  | RENT AND UTILITY | 2014-03-10 | 10 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 187.5 | 1232.75 | 1300
Easter weeks | [5 empty] | Easter
1 | - |  | - |  |  | 2014-03-17 | 1 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 993.5
2 | - |  | - |  |  | 2014-03-24 | 2 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 818.75
3 | - |  | - |  |  | 2014-03-31 | 3 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 1012.5
4 | - |  | - |  |  | 2014-04-07 | 4 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 887.5
5 | - |  | - |  |  | 2014-04-14 | 5 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 1087.5
Summer term weeks | [5 empty] | Summer term
1 | - |  | - |  |  | 2014-04-21 | 1 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 95.75 | 187.5 | 1783.25 | 1125
2 | - |  | - |  |  | 2014-04-28 | 2 | 95.75 | 95.75 | 187.5 | 187.5 | 187.5 | 95.75 | 187.5 | 187.5 | 187.5 | 187.5 | 1599.75 | 1581.25 | Financial Report 3
3 | - |  | - |  |  | 2014-05-05 | 3 | 95.75 | 95.75 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 1691.5 | 0
4 | 5694.3 |  | - |  | RENT | 2014-05-12 | 4 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 187.5 | 1232.75 | 0
5 | - |  | - |  |  | 2014-05-19 | 5 | 187.5 | 187.5 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 95.75 | 187.5 | 187.5 | 1416.25 | 0 | Final financial
6 | - |  | 1650 |  | UTILITY | 2014-05-26 | 6 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 95.75 | 187.5 | 187.5 | 95.75 | 187.5 | 1691.5 | 0
7 | 1898.1 |  | - |  | RENT | 2014-06-02 | 7 | 187.5 | 187.5 | 187.5 | 187.5 | 95.75 | 187.5 | 95.75 | 95.75 | 187.5 | 187.5 | 1599.75 | 0 | Group presentation focus on program and sales
8 | - |  | - |  |  | 2014-06-09 | 8 | 187.5 | 187.5 | 187.5 | 187.5 | 187.5 | 95.75 | 187.5 | 187.5 | 187.5 | 187.5 | 1783.25 | 0
9 | - |  | - |  |  | 2014-06-16 | 9 | 187.5 | 187.5 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 1232.75 | 0
10 | 1898.1 |  | 600 |  | RENT AND UTILITY | 2014-06-23 | 10 | 95.75 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 1049.25 | 0
TOTAL | 15817.5 | + | 3600 | = | 19417.5 | TOTAL |  | 3120.25 | 3095.25 | 3212 | 3074.5 | 2828.5 | 2615.75 | 2966 | 2745 | 2995.25 | 3147.5 | 29800 | 19702.5
[16 empty] | Total= | 29800
[8 empty] | PROJECTION= | 46875
based on 15 hours a week per person
[8 empty] | EXTRA: |  |  |  |  | Totals: |  |  | NO CURRENT INCOME
[8 empty] | Overhead recovery rate (overhead costs/labour hours) |  |  |  |  | 9.55 £/hr
[8 empty] | Chef and Photographer Hire |  |  |  |  | 600
[8 empty] | Marketing - advertisement and promotion |  |  |  |  | 10000 | per year
[8 empty] | Module Prices - text, audio, video, graphics & images |  |  |  |  | 7000 | per module
[8 empty] | Contract value payment upon placement of contract = |  |  |  |  | 1750
[8 empty] | Contract value payment upon handover of module code = |  |  |  |  | 3500 |  |  | Total Maximum Projection
[8 empty] | Contract value payment upon group acceptance of module = |  |  |  |  | 1750 |  |  | 66892.5
Total Realistic Projection
[8 empty] | Projected Sales figures | [7 empty] | 49817.5
Interest Rate = 16.86% APR

## Timesheets
|  | Ankita | Max | James | John | Sam | Paul | Prakurti | Zayyad | Steve | Roger | Actual Cost
Spring term | Week
2014-01-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2014-01-13 | 2 | 100 | 75 | 75 | 75 | 37.5 | 50 | 87.5 | 62.5 | 100 | 37.5 | 700
2014-01-20 | 3 | 100 | 100 | 125 | 125 | 62.5 | 100 | 100 | 100 | 112.5 | 62.5 | 987.5
2014-01-27 | 4 | 187.5 | 187.5 | 187.5 | 50 | 87.5 | 100 | 137.5 | 125 | 50 | 131.25 | 1243.75
2014-02-03 | 5 | 175 | 125 | 125 | 250 | 150 | 100 | 125 | 62.5 | 125 | 62.5 | 1300
2014-02-10 | 6 | 187.5 | 137.5 | 187.5 | 100 | 125 | 175 | 162.5 | 137.5 | 137.5 | 262.5 | 1612.5
2014-02-17 | 7 | 237.5 | 150 | 150 | 265.25 | 112.5 | 137.5 | 175 | 162.5 | 125 | 375 | 1890.25
2014-02-24 | 8 | 112.5 | 162.5 | 150 | 175 | 125 | 150 | 87.5 | 62.5 | 187.5 | 312.5 | 1525
2014-03-03 | 9 | 125 | 275 | 75 | 275 | 125 | 137.5 | 150 | 87.5 | 137.5 | 250 | 1637.5
2014-03-10 | 10 | 75 | 125 | 100 | 175 | 62.5 | 75 | 87.5 | 75 | 225 | 300 | 1300
Easter
2014-03-17 | 1 | 62.5 | 125 | 37.5 | 243.5 | 75 | 75 | 37.5 | 62.5 | 237.5 | 37.5 | 993.5
2014-03-24 | 2 | 50 | 150 | 50 | 131.25 | 37.5 | 50 | 87.5 | 50 | 112.5 | 100 | 818.75
2014-03-31 | 3 | 62.5 | 200 | 75 | 212.5 | 62.5 | 75 | 37.5 | 87.5 | 112.5 | 87.5 | 1012.5
2014-04-07 | 4 | 125 | 125 | 37.5 | 137.5 | 37.5 | 75 | 75 | 75 | 0 | 200 | 887.5
2014-04-14 | 5 | 162.5 | 112.5 | 100 | 137.5 | 12.5 | 75 | 62.5 | 112.5 | 112.5 | 200 | 1087.5
Summer term
2014-04-21 | 1 | 75 | 125 | 50 | 162.5 | 50 | 112.5 | 187.5 | 62.5 | 187.5 | 112.5 | 1125
2014-04-28 | 2 | 162.5 | 187.5 | 187.5 | 193.75 | 112.5 | 50 | 175 | 162.5 | 175 | 175 | 1581.25
2014-05-05 | 3 | [10 empty] | 0
2014-05-12 | 4 | [10 empty] | 0
2014-05-19 | 5 | [10 empty] | 0
2014-05-26 | 6 | [10 empty] | 0
2014-06-02 | 7 | [10 empty] | 0
2014-06-09 | 8 | [10 empty] | 0
2014-06-16 | 9 | [10 empty] | 0
2014-06-23 | 10 | [10 empty] | 0
| Total | 2000 | 2362.5 | 1712.5 | 2708.75 | 1275 | 1537.5 | 1775 | 1487.5 | 2137.5 | 2706.25 | 19702.5
|  | 4799.75 | [5 empty] | 2276.25 |  |  |  | 4799.75
|  | 7.6796 | [9 empty] | 3750
1049.75
Note on I37: Sam Beedell: overspend on labour for spring term
Note on C38: Sam Beedell: hours worked on average over easter
Note on M39: Sam Beedell: over spend on labour during easter break