## Sheet1
Risk | Probability | Impact | P X I | Resolution
Failure to meet a requirement. | 4 | 5 | 20 | Control: Have regular review meetings where requirement conformity is checked. Make sure that the design and the development of the product is organised in a way that simplifies rollback and re-implements the missing requirements with as little modification to other parts as possible.
Employees producing work that is below the expected standard. | 4 | 4 | 16 | Avoidance: Have a system to review work done by each member. Control: Hold separate meetings with the members in question. Transference: If even after repeated counselling there is no change, talk to the board members (the supervisor and/or second supervisor) to take further action.
QA Metrics not being measured regurarly | 4 | 4 | 16 | Control: Have a weekly review system for employees
Deadline overdue on deliverables. | 3 | 5 | 15 | Avoidance: Have a good and appropriate project plan Control: Have regular project plan review meetings in which possible overruns can be identified and rescheduling can be considered if necessary.
Deliverable not up to company standards | 3 | 5 | 15 | Avoidance: Have a QA system in check. Control: Have a standards review meeting to ammend the oversights in the deliverable.
Failure in talks for contract agreement | 3 | 5 | 15 | Control: Try and negotiate term and conditions to further the transactions. Transference: Talk to other groups.
Conflict within the contract | 3 | 5 | 15 | Avoidance: Have a clear and transparent contract agreement. Control: Reach a peaceful agreement with other group to resolve conflict. Transference: Get in touch with project coordinator if all else fails.
Modules sold unacceptable to buyer | 3 | 5 | 15 | Avoidance: Keep an open dialogue with the other group to understand requirements. Control: Have a meeting with other group to identify and modify unacceptable elements.
Some group members don’t get along with each other. | 3 | 4 | 12 | Control: Try to resolve any issues that group members might have. Acceptance: Consider assigning and delegating tasks to minimise disruption within the group as a whole.
Finding out late during the project that one member has a lot more work to do than the others. | 3 | 4 | 12 | Avoidance: Review the workload for each member regularly to make sure there is parity in the amount of work done by each person.
Negative attitude/ lack of confidence in employees | 3 | 4 | 12 | Avoidance: Maintain a positive working environment. Control: Have separate meetings to reassure and boost morale of employees.
Documention not being produced on time | 3 | 4 | 12 | Avoidance: Have an early warning system. Control: Follow up on employees not producing documents and hold meetings with them if necessary .
Disagreement with other groups on joint assignments | 3 | 4 | 12 | Control: Hold meetings with other groups to find a resolve.
The prolonged absence of a team member. | 2 | 4 | 8 | Control: Have more than one team member trained to do any task. Acceptance: Adjust schedules as appropriate.
Conflicts within pre-determined PWS | 2 | 4 | 8 | Control: Have an intergroup meeting to overcome these conflicts
Modules bought not up to company standards and coding practices | 2 | 4 | 8 | Avoidance: Keep an open dialogue with the other group to make sure they understand the requirements.
PWS not being adhered to | 2 | 3 | 6 | Control: Hold a meeting to identify and correct breaches of the PWS