## Buisness Projection
BUSINESS PLAN AS AT 21/02/2014
| OVERHEAD | [6 empty] | LABOUR
| RENT: £/wk(so) | 632.7 | IT & UTILITIES: £/wk(s) | 150 |  |  |  | Ankita | Max | James | John | Sam | Paul | Prakurti | Zayyad | Steve | Roger | Projected Total | Actual total
Spring term weeks | RENT DUE |  | PAYMENT DUE |  |  | Spring term | Week
1 | - |  | - |  |  | 2014-01-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | - |  | - |  |  | 2014-01-13 | 2 | 100 | 75 | 75 | 75 | 37.5 | 50 | 87.5 | 62.5 | 100 | 37.5 | 700 | 700
3 | - |  | - |  |  | 2014-01-20 | 3 | 100 | 100 | 125 | 125 | 62.5 | 100 | 100 | 100 | 112.5 | 62.5 | 987.5 | 987.5 | Functional Spec due
4 | 2530.8 |  | - |  | RENT | 2014-01-27 | 4 | 187.5 | 187.5 | 187.5 | 50 | 87.5 | 100 | 137.5 | 125 | 50 | 131.25 | 1243.75 | 1243.75 | QA manual due; Business Plan
5 | - |  | - |  |  | 2014-02-03 | 5 | 187.5 | 187.5 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 1324.5 | 1175 | PWS
6 | - |  | 900 |  | UTILITY | 2014-02-10 | 6 | 187.5 | 187.5 | 187.5 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 1416.25 | 1450 | Tender presentation; Financial Report 1
7 | 1898.1 |  | - |  | RENT | 2014-02-17 | 7 | 95.75 | 95.75 | 95.75 | 187.5 | 187.5 | 95.75 | 187.5 | 187.5 | 187.5 | 187.5 | 1508 | 1715.25 | Contracts | Integration for first JIRA sprint
8 | - |  | - |  |  | 2014-02-24 | 8 | 187.5 | 187.5 | 187.5 | 95.75 | 187.5 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 1416.25 | 1325 | Financial report 2
9 | - |  | - |  |  | 2014-03-03 | 9 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 1141 | 0 | First Iteration complete; documents sent to supervisor; Integration and testing
10 | 1898.1 |  | 450 |  | RENT AND UTILITY | 2014-03-10 | 10 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 187.5 | 1232.75 | 0
Easter weeks | [5 empty] | Easter | [12 empty] | 0
1 | - |  | - |  |  | 2014-03-17 | 1 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 0
2 | - |  | - |  |  | 2014-03-24 | 2 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 0
3 | - |  | - |  |  | 2014-03-31 | 3 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 0
4 | - |  | - |  |  | 2014-04-07 | 4 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 0
5 | - |  | - |  |  | 2014-04-14 | 5 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 750 | 0
Summer term weeks | [5 empty] | Summer term | [12 empty] | 0
1 | - |  | - |  |  | 2014-04-21 | 1 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 957.5 | 0
2 | - |  | - |  |  | 2014-04-28 | 2 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 957.5 | 0 | Financial Report 3
3 | - |  | - |  |  | 2014-05-05 | 3 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 187.5 | 187.5 | 95.75 | 95.75 | 1232.75 | 0
4 | 5694.3 |  | - |  | RENT | 2014-05-12 | 4 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 957.5 | 0
5 | - |  | - |  |  | 2014-05-19 | 5 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 957.5 | 0 | Final financial
6 | - |  | 1650 |  | UTILITY | 2014-05-26 | 6 | 95.75 | 95.75 | 95.75 | 95.75 | 187.5 | 95.75 | 187.5 | 187.5 | 95.75 | 95.75 | 1232.75 | 0
7 | 1898.1 |  | - |  | RENT | 2014-06-02 | 7 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 957.5 | 0 | Group presentation focus on program and sales
8 | - |  | - |  |  | 2014-06-09 | 8 | 187.5 | 187.5 | 95.75 | 95.75 | 187.5 | 95.75 | 187.5 | 187.5 | 187.5 | 95.75 | 1508 | 0
9 | - |  | - |  |  | 2014-06-16 | 9 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 957.5 | 0
10 | 1898.1 |  | 600 |  | RENT AND UTILITY | 2014-06-23 | 10 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 95.75 | 957.5 | 0
TOTAL | 15817.5 | + | 3600 | = | 19417.5 | TOTAL |  | 2661.5 | 2636.5 | 2569.75 | 2432.25 | 2645 | 2157 | 2782.5 | 2561.5 | 2536.5 | 2413.5 | 25396 | 8596.5
[16 empty] | Total= | 25396
[8 empty] | PROJECTION= | 46875
based on 15 hours a week per person
[8 empty] | EXTRA: |  |  |  |  | Totals:
[8 empty] | Overhead recovery rate (overhead costs/labour hours) |  |  |  |  | 9.55 £/hr
[8 empty] | Chef and Photographer Hire |  |  |  |  | 600
[8 empty] | Marketing - advertisement and promotion |  |  |  |  | 10000 | per year
[8 empty] | Module Prices - text, audio, video, graphics & images |  |  |  |  | 7000 | per module
[8 empty] | Contract value payment upon placement of contract = |  |  |  |  | 1750
[8 empty] | Contract value payment upon handover of module code = |  |  |  |  | 3500
[8 empty] | Contract value payment upon group acceptance of module = |  |  |  |  | 1750
Projected Sales figures
Interest Rate = 16.86% APR
NO CURRENT INCOME

## Timesheets
|  | Ankita | Max | James | John | Sam | Paul | Prakurti | Zayyad | Steve | Roger | Actual Cost
Spring term | Week
2014-01-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2014-01-13 | 2 | 100 | 75 | 75 | 75 | 37.5 | 50 | 87.5 | 62.5 | 100 | 37.5 | 700
2014-01-20 | 3 | 100 | 100 | 125 | 125 | 62.5 | 100 | 100 | 100 | 112.5 | 62.5 | 987.5
2014-01-27 | 4 | 187.5 | 187.5 | 187.5 | 50 | 87.5 | 100 | 137.5 | 125 | 50 | 131.25 | 1243.75
2014-02-03 | 5 | 175 | 125 | 125 | 250 | 150 | 100 |  | 62.5 | 125 | 62.5 | 1175
2014-02-10 | 6 | 187.5 | 137.5 | 187.5 | 100 | 125 | 175 |  | 137.5 | 137.5 | 262.5 | 1450
2014-02-17 | 7 | 237.5 | 150 | 150 | 265.25 | 112.5 | 137.5 |  | 162.5 | 125 | 375 | 1715.25
2014-02-24 | 8 |  | 162.5 | 150 | 175 | 125 | 150 |  | 62.5 | 187.5 | 312.5 | 1325
2014-03-03 | 9 | [10 empty] | 0
2014-03-10 | 10 | [10 empty] | 0
Easter
2014-03-17 | 1 | [10 empty] | 0
2014-03-24 | 2 | [10 empty] | 0
2014-03-31 | 3 | [10 empty] | 0
2014-04-07 | 4 | [10 empty] | 0
2014-04-14 | 5 | [10 empty] | 0
Summer term
2014-04-21 | 1 | [10 empty] | 0
2014-04-28 | 2 | [10 empty] | 0
2014-05-05 | 3 | [10 empty] | 0
2014-05-12 | 4 | [10 empty] | 0
2014-05-19 | 5 | [10 empty] | 0
2014-05-26 | 6 | [10 empty] | 0
2014-06-02 | 7 | [10 empty] | 0
2014-06-09 | 8 | [10 empty] | 0
2014-06-16 | 9 | [10 empty] | 0
2014-06-23 | 10 | [10 empty] | 0
| Total | 987.5 | 937.5 | 1000 | 1040.25 | 700 | 812.5 | 325 | 712.5 | 837.5 | 1243.75 | 8596.5